## Tabulations
(All numbers rounded to nearest whole dollars)
FUNDING SOURCES - MEASURE T
Total bond sales to date |  |  | 70000000
Cost of Issuance |  |  | -285000
Net Bond Proceeds |  |  | 69715000
Received from bond Refunding
Interest Received
Net gain (loss) in funds held by Mo Co Treasurer
TOTAL FUNDS FROM MEASURE T |  |  | 69715000
Project Titles | Project Number | Series | Project Budget | Budget w/Contractor contract | Expenses 16/17 | Expenses 17/18 | Expenses 18/19 | Expenses 19/20 | Total Bond Expenses | Project Balance | Notes
Series A
Minor Renovation of Building N for Relocation of Respiratory Care and EMT Programs/Swing Space | 880000-01 | A | 213845 |  | 14407.25 | 13850 | 29741.33 |  | 57998.58 | 155846.42
County Election costs for November 2016 ballot | 880000-01 | A | 341515 |  | 341515 | 0 | 0 | 0 | 341515 | 0
Master Planning for Measure T | 880000-01 | A | 797000 |  | 0 | 529331 | 0 | 0 | 529331 | 267669
Soledad Education Center | 880100-01 | A | 13180636 |  | 0 | 191470.69 | 590920.99 | 28219.09 | 782391.68 | 12398244.32 | *
Main Campus Nursing and Health Science | 880200-01 | A | 21207321 |  | 0 | 172762.64 | 1118745.85 | 92758.37 | 1291508.49 | 19915812.51 | *
Solar Panel Relocation | 880200-01 | A | 621945.01 | 621945 | 0 | 0 | 537657.93 | 0 | 537657.93 | 84287.08 | *,2. | Completed
North County Education Center | 880300-01 | A | 10890176 |  | 0 | 66131.17 | 111163.33 | 48850 | 177294.5 | 10712881.5 | *
Main Campus Buildings D & E Renovation | 880400-01 | A | 14382866 | 20760249 | 2886.75 | 9872.93 | 645631.57 | 73510 | 658391.25 | 13724474.75 | *
King City Education Center Expansion | 880500-01 | A | 8175155 |  | 0 | 38526.65 | 455412.55 | 16998.52 | 493939.2 | 7681215.8 | *
Parking - angleStriping |  |  |  | 75000
Replace Phone System | 881100-01 | A | 422026 |  | 109180.79 | 309126.84 | 0 | 0 | 418307.63 | 3718.37 |  | Completed
Phone system 2018-19 | 881100-56400 | A | 185716 |  | 0 | 0 | 145715.25 | 40910 | 186625.25 | -909.25
Refresh Internet System | 881100-56226 | A | 701529 |  | 0 | 0 | 0 | 197830.47 | 197830.47 | 503698.53
Project Salary/Benefits/Gen'l Ops/Legal | 801/659 |  |  |  | 5968.31 | 147726.8 | 40730.63 | 11502.05 | 194425.74 | -194425.74 | 1
|  |  | 71119730.01 |  | 473958.1 | 1478798.72 | 3675719.43 | 510578.5 | 5867216.72 | 65252513.29
Series B Projects Paid with Series A-To Be Reimbursed
Main Campus Building H Roof Replacement | 880700-01 | B | 904873.4 |  |  | 904873.4 | 0 | 0 | 904873.4 | 0 | 3 | Completed
Main Campus Building K Roof Replacement | 880800-01 | B | 465480 |  |  | 465480 | 0 | 0 | 465480 | 0 |  | Completed
Property Acquistion-Castroville | 880300-01 | B | 850000 |  |  | 42500 | 807981.97 | 0 | 850481.97 | -481.97 |  | Completed | 24,000 PGE +
Main Campus Bldg K - Ticket Booth/Lobby reno | 880800-01 | B | 516750 |  |  | 167902 | 348848.07 | 0 | 516750.07 | -0.07 | *, 4 | 999.99
Totals |  |  | 73856833.41 |  | 473958.1 | 3059554.12 | 4832549.47 | 0 | 8604802.16 | 65252031.25
Series B and C (future issuances) |  |  | 97000000
Main Campus Building N Renovation
Main Campus Buildings F, G, H Renovation | 880700-03 | C | 13045 |  |  |  | 13045 |  | 13045 | 0 | 5 | 60120
Main Campus Building K Renovation
Main Campus Building J Renovation
Main Campus Building B 2nd Flr Renovation | 8802500-02 | B | 2000000 |  |  |  | 117177.99 |  | 117177.99 | 1882822.01 | 6
Alisal Campus Additional Classrooms/Labs
Partner with high schools to improve science classrooms/labs
* Includes ALL anticipated costs, including but not limited to design, DSA, construction, contingencies, testing/inspection, etc., as most recently adjusted, which will be paid for out of Measure T Funds. | Note: Project budgets are estimates and will not be final until projects are bid and contracts awarded.
1. Row 26 - Admin costs are allocated to each
individual project. On spreadsheet they are pulled together in one line item. (2/2018)
*, 2. Row 18 break out of the Solar relocation
portion of the Nursing building. This sub-portion of the
Nursing project orig. projection of $560,000 now $621,945 due to
steel costs escalating. (6/2018)
3. Row 30 Orig budget $888,226 increased due to
CO#1 $16,647.40 (6/2018)
*, 4. Row 33 Figure includes not incl. NTBid The Californian $999.00 Fund 44 (6/2018)
5. Row 41 $60,120 HGHB, Facilities Planning & Consulting Services & M3
to produce FPP for submission to Chancellors office for possible matching funds Fund 44
LTD Haz Mat rpt $13,045 for FPP/Series C - completed early (Apr/May 2019) Fund 46
6. Row 44 To date architect fees for re-design of second floor (4/2019)
Note on O11: Dawn Henry: Working draft for the May 1 Board Mtg. Exhibit G - to Board May 1 (4/16/18)
Note on R13: Dawn Henry: Swing spce figure in F13 are current expenses for swing space. $$ to cover taken from surplus in gkk master planning budget. Figure O15 is actual remaining bal of master planning

## Notes
# | Note
* | Includes all anticipated cost, including but not limmited to design, DSA, construction, contingencies, testing/
inspection, etc., as most recently adjusted, which will be paid for out of Measure T Funds,
11/30/17: Expenses - Draws 1 and 2 for each Building H($355,808.90 + $53,863.23) and K($227,849.58 &$189.810.30) and 2
invoices for phones - one for implementation work ($3217.00) and the second for voice over work for system messages ($720)
12/9/17: Lozano Smith legal invoice ($11,753) for review, document production of contracts for Design/Build mode of delivery; $203,986.07 total expenditures to date for phone system too Communication Strategies and Extelesis Corp - included on this update at completion of transfer from Fund 41 (used prior to sale of bonds and Fund46 set up)
3/27/18: The Californian Notice to Bidder - publication for PAR project $999.42
4/27/18: $15000 for swing work vendors deducted from balance of Master Planning budget balance is now 266,544
8/9/18: $24,000 received from PG&E for Construction Lease of Temblardara St property
9/27/18: $26,700 deducted from Master Planning budget balance - Now $227,619 for gkk addt'l structure and CGS survey