## PPA
PPA Calendar 2024-25
Date | Activity | Responsible People/Groups
September
September 3rd | Approval of FY 2024-25 Budget | BOT
End of Month | Budget update to College Council and IRC | CBO
September 16th | Deadline for PPA budget requests for activities to be undertaken in and positions to begin FY 2025-26 to be entered into Nuventive. | Disciplines/Service Areas
October
October 7th | Submit prioritized budget requests for their area to the VP’s office after consultation with everyone in their area. | Deans/Directors
October 21st | Submit lists of prioritized requests for their division to the CBO after meeting with all the Deans/Directors in their area. | VPs
November
November 8th | Submit recommendations to VPAA/VPSA for full-time faculty positions to begin Fall 2025. | Full-Time Faculty Hiring Committee
End of Month | Reviews top budget request to recommend funding list based on available funding (info item) | PPO&A
December
December 6th | Discussion of prioritized budget requests for all divisions to IRC for recommendation to Superintendent/President | CBO
December 15th | Superintendent/President communicates the list of approved budget requests, including full-time faculty and staff postiions, to the college | S/P
January
End of Month | Funds released from 2024-25 budget, or other sources, for approved budget requests. | Controller
February
February 4th | PPA templates made available to academic disciplines (eLumen) and service areas (Nuventive). | PPA Specialist
March
March 21st | PPA reports (in eLumen or Nuventive) and budget requests for activities to be undertaken in and positions to begin FY 2026-27 (final version submitted Fall 2025) are due. | Disciplines/Service Areas
April
April 11th | Completed review of PPA reports given to constituents and summary given to appropriate VP. | Deans/Directors
April 28th | Executive reports given to college community | VPs
May
End of the Semester | Budget overview for 2025-26 presented to College Council and IRC | CBO
May 30th | PPA reports and executive reports posted on college website | IRC Director