## Sheet1
HCCD Capital Improvement Program
Measure T Funding |  | 167000000 | Sources
~Interest Funding through Dec. 2019 |  | 3021690
Potential 2020 State GO Bond Matching Funds Conditions: Statewide Nov election and award |  | 13866000
Potential State High School Matching Funds |  | 4500000
Total Funding If Matches are Met |  | 188387690
Unexpended 10% Owner's Contingency |  | tbd
Phase I (2018-2022) | 2015 Planning Budget | 2016 Project Budget-Architect Analysis |  | Engineer Estimate | Construction Contract | 10% Owner's Contingency | Estimated Soft Costs ** | Estimated Total Cost | Budget vs Actual | Status
South County Education Center (Soledad) * | 13750000 | 13180636 |  | $11.5M - $11.8M | 12512500 | 1237500 | 2065090 | 15815090 | -2634454 | Construction
Secondary Effects: MST Bus Stop | [7 empty] | tdb
King City Education Center Expansion * |  | 8175155 |  | $6,71,000 | 8648916 | 864891.6 | 2530701.4 | 12044509 | -3869354 | Construction
North Monterey County Education Center (Castroville) |  | 10890176 |  | Design-Build | 9593046 | 959304.6 | 1693526 | 13090065 | -2199889 | Architect CD
Architect Fees |  |  |  |  | 767444 | 76744.4 |  |  | 0
Main Campus Buildings D & E + Quad Renovation * |  | 14382866 |  | 13762033 | 13755000 | 1375500 | 2299976 | 17430476 | -3047610 | Construction
Hartnell College Nursing & Health Science |  | 21207321 |  | 21329797 | 19474711 | 1944471 | 3309733 | 24728915 | -3521594 | Construction
Secondary Effects Remodel Building B |  | 2000000 |  | 1500000 |  |  | 500000 | 2000000 | 0 | DSA
Phone System & Internet Refresh |  | 422026 | [5 empty] | 422026 | 0 | Actual & Complete
Master Architect (Planning, Standards, Budget) |  | 750000 | [5 empty] | 529331 | 220669 | Actual & Complete
Solar Panel Relocation |  | 621945.01 | [5 empty] | 621945.01 | 0 | Actual & Complete
Main Campus Building H Roof Replacement |  | 904873.4 | [5 empty] | 904873.4 | 0 | Actual & Complete
Main Campus Building K Roof Replacement |  | 465480 | [5 empty] | 465480 | 0 | Actual & Complete
Property Acquistion-Castroville |  | 850000 | [5 empty] | 850000 | 0 | Actual & Complete
Main Campus Bldg K - Ticket Booth/Lobby reno |  | 516750 | [5 empty] | 516750 | 0 | Actual & Complete
Subtotal Phase I |  | 74367228.41 |  |  |  | 6458411.6 |  | 89419460.41 | -15052232
0
Phase II (2021-2025)
New Building Alisal Campus | 13750000 | 13735281 | [5 empty] | 13735281 | 0
Bldg J (Visual Arts) * | 9440625 | 9442433 | [5 empty] | 9442433 | 0
Bldg K (Performing Arts) * | 16366875 | 16372248 | [5 empty] | 16372248 | 0
Football Fields | 2000000 | 2000000 | [5 empty] | 2000000 | 0
High School Partnerships | 2250000 | 2250000 | [5 empty] | 2250000 | 0
Subtotal Phase II |  | 43799962 | [5 empty] | 43799962 | 0
Phase III (2023-end)
Bldg N (Merrill Hall) * | 16251375 | 16188436 | [5 empty] | 16188436 | 0
Bldg F,G,H (Athletics Building)* (State Match) | 27756375 | 27733379 | [5 empty] | 27733379 | 0
High School Partnerships | 2250000 | 2250000 | [5 empty] | 2250000 | 0
Infrastructue Upgrades (Sustainability, Energy Efficiency,Technology, Safety) |  | 2660995 | [5 empty] | 2660995 | 0
Subtotal Phase III |  | 48832810 | [5 empty] | 46171815
Total Projected Measure T Funding |  | 167000000.41 | [5 empty] | 179391237.41 | -12391237
Total Projected HCCD Capital Improvement Program Cost |  | 188387690 | [5 empty] | 179391237.41 | 8996452.59
*=Not completed with Measure H funds
Soft costs include Architectural and Engineering fees, DSA Permiting and local Permitting, Project Management, Legal, Inspectors of Record, Bond Issuance…

## Sheet2
Phase I, II, III | 2016 Project Budget-Architect Analysis | Estimated Total Cost | Budget vs Actual & Estimated
Total Projected HCCD Capital Improvement Program Cost | 188387690 | 179391237.41 | 8996452.59